## Bugs & Fixes
# | Area | Issue / Request | Root Cause | Fix / What Was Done | Status
1 | Challenge – Tests | Challenge test suite wouldn't run at all | Harness passed map literals where ChallengeShopifyVariant objects were required -> compile error, 0 tests ran | Constructed ChallengeShopifyVariant(...) in the harness | Fixed
2 | Challenge – Tests | Scoring test failed | Passed a stale pre-approval submission object into the scorer (reads reviewStatus off the object) | Re-fetch the submission after approval | Fixed
3 | Challenge – Tests | Delete test failed | Seeded a registrationOpen challenge; deleteChallenge only allows drafts | Seed a draft challenge in the test | Fixed
4 | Challenge – Logic | Cross-challenge baseline leak | submission_review_service._submit checked hasBaseline across ALL challenges (userId only, no challengeId filter) -> approved baseline in challenge A unlocked weekly/final in B | Added streamSubmissionsByParticipantAndChallenge (scoped query) + switched _submit to it | Fixed
5 | Challenge – Rules | Join failed with permission-denied | notifications create rule was admin-only; participant creating own 'joined' notification denied | Rule: allow self-create (recipientUserId==uid); + best-effort try/catch on join notification | Fixed
6 | Challenge – Rules | Payment recovery re-submission would be denied | Recovery branch's hasOnly list omitted latestPaymentRecordId, which resubmitPaymentProof sets | Added latestPaymentRecordId (+ paymentMethod) to the recovery branch | Fixed
7 | Challenge – Rules | isAdmin() crashed for many users | data.role read threw 'Property is undefined' for user docs with no role/isAdmin field | Use data.get('role','') / data.get('isAdmin',false) | Fixed
8 | Challenge – Rules | Leaderboard permission-denied for participants | Leaderboard read all participants (admin-only list) + all submissions (owner/admin only) | Sanitized public leaderboard collection (read: signed-in, write: admin) | Fixed
9 | Challenge – Rules | Admin 'Utilities' reminder buttons -> permission-denied | Reminder dedupe reads participants' notifications; notifications read rule had no admin exception | Rule: allow read if isAdmin() ¦¦ own | Fixed
10 | Challenge – Rules | Participants could self-set winner fields | finalPlacement/awardLabel not protected | Added them to the participant sensitive-field blocklist | Fixed
11 | Challenge – Logic | formatName RangeError | UserRepository.formatName did substring(0,4) on ids shorter than 4 chars | Length-guarded the substring | Fixed
12 | Challenge – Logic | Failed notification write crashed a successful join | notifyParticipantJoined awaited inline; any failure broke the flow | Wrapped in best-effort try/catch | Fixed
13 | Challenge – Logic | Leaderboard insights RangeError / StateError | indexWhere -1 and firstWhere with no orElse in insights provider | Rewrote insights provider for the sanitized standings | Fixed
14 | Challenge – Leaderboard | Leaderboard empty despite approved data | Sanitized snapshot is only written on admin review; older approvals never published it | Added admin 'Refresh Leaderboard' action (backfill) on challenge detail | Fixed
15 | Challenge – Weekly | No server guard on weekly cadence; add 'next check-in' info | Only UI gated one-per-week; no server guard; no countdown shown | Added server-side duplicate-week guard + 'Week N check-in open / next in X days' banner | Fixed / Added
16 | Challenge – Winners | Winner selection didn't exist (Rule Book §9) | Official scores computed but no declare-winners / results flow | Built Phase 1: ChallengeWinner model, WinnerSelectionService (auto-rank, body-fat first), admin Select Winners screen, participant winners banner, notifications, tests | Built
17 | App – iOS UX | Keyboard couldn't be dismissed; submit button hidden; fields didn't expand | Fixed-height bottom sheet / scroll views with no keyboard handling; multiline fields fixed height | Swipe/tap-to-dismiss, keyboard-inset bottom padding, growing multiline fields + char limits (AI coach wizard + 4 challenge submission screens) | Fixed
18 | App – Auth | No 'Forgot password?' on the profile re-login form | Profile screen's inline login form lacked it | Added 'Forgot password?' + reset dialog | Fixed
19 | App – Auth | Reset email showed one generic error for all failures | sendPasswordReset threw a single generic message | Distinguish EMAIL_NOT_FOUND / INVALID_EMAIL with friendly text | Fixed
20 | App – Home | Reorder home blocks | Requested layout change | Swapped 'Your Challenge' above 'Gear Up Your Fitness Journey' | Done
21 | App – Food search | Search suggestions stayed after tapping Search / elsewhere | In-flight autocomplete re-opened the dropdown after submit (only checked text match); no tap-outside dismiss | Require field focus before re-showing suggestions + tap-results-to-dismiss | Fixed
22 | Push | Challenge notifications weren't push (in-app only) | No delivery mechanism wired | Cloud Function sendChallengePush (Firestore onCreate -> OneSignal), participant-only | Built / Deployed
23 | Push | OneSignal couldn't target users | OneSignalService.setUser was never called -> no external_id | Wired setUser (Firebase uid) / clearUser in AuthService | Fixed
24 | Push | OneSignal App ID mismatch | secrets.dart had a stale app id (f7c2b...) | Aligned app + function to 729c9710 | Fixed
25 | Push | OneSignal push 401 (invalid API key) | Legacy endpoint + Basic auth for a new os_v2_app_ key; and REST key mistyped in the secret | Use api.onesignal.com + 'Key' auth; re-set the correct REST key secret | Fixed
26 | Push | Push didn't arrive on emulator | Emulator had no Google Play Services (FCM); iOS simulators can't receive push | Explained: test on a real device / Google Play image | Explained
27 | Push | iOS push not working | APNs not configured in OneSignal | Provided checklist: upload APNs .p8 (token auth) to OneSignal; verify capabilities; test on real iPhone | Explained (config)
28 | Auth – Login | Shopify / AI-coach users can't log into the app | App only does Firebase email/password; coach auto-provisions Firebase accounts with a machine 'bridge password' (or a real pw that diverged from Shopify) | Built Shopify bridge login: direct -> Shopify validate -> syncShopifyPassword Cloud Function sets Firebase pw = Shopify pw -> login. Wired into onboarding + profile | Built / Deployed
29 | PENDING | Stuck upload spinner | _isUploading not reset if a photo upload throws (4 submit providers) | Not yet fixed | Pending
30 | PENDING | Leaderboard has no tie-breaker | Equal scores sort non-deterministically | Not yet fixed | Pending
31 | PENDING | Push tap-through ignores deepLink | Click handler only routes shop/product; opens app, not the target challenge screen | Not yet fixed | Pending
32 | PENDING | Consistency score divides by fixed 5 | MVP placeholder instead of the real expected check-in count | Known limitation | Pending